## Sheet1
Id | Type | Description | Status | Reported Date/Time | Completed | Comments
1 | Bug | When content-left-header-menu is closed the margin bottom doesn’t revert back to 0px | Pending | 23 March 2018/ 1440
2 | Story | Add swipe to pagination if possible | Pending | 24 March 2018/ 1229
3 | Enhancement | Move Menus to their respective button slots | Pending | 24 March 2018/ 1233
4 | Story | Folder Path on title of content left div | Pending | 24 March 2018/ 1233
5 | Enhancement | Rename Content left div to some proper ID | Complete | 24 March 2018/ 1233 | 24 March 2018/ 2215 | Id to class of #content element - completed on 24 March 2018/ 1855 Need to modify JS for the same - done on 24 March 2018/2202 Also deleted the commented code in activity.html - completed on 24 March 2018/ 1855
6 | Enhancement | Remove/delete commented code in activity.html | Pending | 24 March 2018/ 1240
7 | Enhancement | Initialize window.localStorage with data for CRUD operation | Pending | 24 March 2018/ 2037
8 | Bug | scroll content-div-mid to last item when new item is added | Pending | 24 March 2018/ 2202
9 | Story | add local storage | Pending | 25 March 2018/ 1500
10 | Enhancement | change inline to flex | Pending | 25 March 2018/ 1500 |  | modified content-div-header in second content
11 | Story | Create Mongo DB schema | Pending | 25 March 2018/ 1500
12 | Story | Create Search box in content 2 | Pending | 07 April 2018/ 1700 | 07 April 2018/ 1905 | created text box and implemented show hide function for search button
13 | Bug | unable to type due to resizing | Complete | 08 April 2018/ 1610 | 08 April 2018/1650 | cannot place display none for input in resize function, resized .span-icon, .span-text